## Sheet1
Location | Make | Size | Temp | Comments | Date | Comments | Make | Temp. Celci
Kitchen Ground floor | Reliance | 15 |  | Tap broke, no temp. | 09.03.21 |  | Reliance | 40
Bathroom Ground floor | Reliance | 15 | 40 |  | 09.03.21 |  | Reliance | 41
Room 2 | Ausi mix | 15 |  | No Hot water | 09.03.21 |  | Ausi mix | 42
Disabled WC ground floor | Ausi mix | 15 | 42 | Failed fail safe test | 09.03.21 | TMV replaced | Imix | 42
Room 3 | Sirrus | 15 | 39 | Failed fail safe test | 09.03.21 | TMV replaced, isos replaced | Imix | 40
Room 4 | Ausi mix | 15 |  | No hot water | 09.03.21 | Sink removed by OTCS
Staff toilet | Bristan shower |  | 39 |  | 09.03.21 |  | Bristan shower | 39
Staff toilet | Ausi mix | 15 | 49 |  | 09.03.21 |  | Ausi mix | 41
Ground floor toilet/store | Reliance | 15 | 41 |  | 15.03.21 |  | Relaince | 41
Kitchen 1st floor 1 | Imix | 15 | 41 |  | 09.03.21 |  | Imix | 42
Toilet 1 1st floor | Ausi mix | 15 | 39 |  | 09.03.21 | Flexis replaced | Ausi mix | 39
bathroom 1 1st floor | Imix | 15 | 42 | Failed fail safe test | 09.03.21 | TMV replaced | Imix | 40
Room 6 | Ausi mix | 41 | 42 | Failed fail safe test | 09.03.21 | TMV replaced | Imix | 42
Room 7 | Ausi mix | 15 |  | No hot water | 09.03.21 | TMV replaced | Imix | 41
Room 5 | Ausi mix | 15 | 39 | Failed fail safe test | 09.03.21 | TMV replaced | imix | 41
Room 8 | Ausi mix | 15 | 38 | Failed fail safe test | 09.03.21 | TMV replaced | Imix | 40
Room 13 | ? | 15 | 43 | Failed fail safe test | 19.03.21 | TMV replaced, Isos replaced | Imix | 39
Room 9 | Ausi mix | 15 |  | Wate to sink isolated as taps are broke | 12.03.21 | TMV replaced | Imix | 43
Room 12 | Ausi mix | 15 | 39 |  | 12.03.21 | TMV replaced | Imix | 39
Room 11 | Ausi mix | 15 | 40 | Failed fail safe test | 12.03.21 | TMV replaced | Imix | 40
Room 10 | Ausi mix | 15 |  | No hot water | 19.03.21 | Isos replaced | Ausi mix | 40
Toilet 2 1st floor | Ausi mix | 15 |  | No hot water | 12.03.21 | TMV replaced, Trap replaced | Imix | 40
Bathroom 2 1st floor | ? | 22 |  | No hot water | 12.03.21 |  | ? | 40
Bathroom 2 1st floor | Reliance | 15 |  | No hot water | 12.03.21 | TMV replaced | Imix | 39
Shower room 1st floor | Thermo shwr |  |  |  | 09.03.21 |  | Thermo shower | 39
Kitchen 1st floor 2 | Reliance | 15 | 41 |  | 12.03.21 |  | Relaince | 41
Kitchen 2nd floor 1 | Reliance | 15 |  | No hot water | 12.03.21 |  | Relaince | 43
Toilet 4 | Ausi mix | 15 |  | No hot water | 12.03.21 | TMV replaced | Imix | 42
Bathroom 1 2nd floor | Ausi mix | 15 |  | No hot water | 12.02.21 | TMV replaced | Imix | 41
Room 15 | Ausi mix | 15 | 42 | 2x Ball fix needed | 19.03.21 | Isos replaced | Ausi mix | 42
Room 16 | Ausi mix | 15 | 38 | Failed fail safe test | 15.03.21 | TMV replaced, Isos replaced | Ausi mix | 39
Room 14 | Ausi mix | 15 | 40 | Failed fail safe test | 12.03.21 | TMV replaced | Imix | 40
Room 17 | Ausi mix | 15 |  | No hot water | 15.03.21 | TMV replaced , Isos replaced | Imix | 41
Room 18 | Imix | 15 | 42 | Failed fail safe test | 15.03.21 | TMV replaced | Imix | 42
Room 22 | Ausi mix | 15 | 43 | Failed fail safe test | 15.03.21 | TMV replaced | Imix | 40
Room 19 | Ausi mix | 15 |  | No hot water | 15.03.21 | TMV replaced | Imix | 39
Room 21 | Ausi mix | 15 | 43 | Failed fail safe test | 15.03.21 | TMV replaced | Imix | 42
Room 20 | Ausi mix | 15 |  | No hot water | 15.03.21 | Room im bad condition, no access. | Ausi mix | 42
Toilet 6 | Ausi mix | 15 | 53 | Cannot adjust Temp. New TMV required | 15.03.21 | TMV replaced | Imix | 40
Bathroom 2 | Imix | 15 |  | No hot water | 15.03.21 | TMV replaced | Imix | 41
Bathroom 2 | ? | 22 |  | No hot water | 15.03.21 |  | ? | 40
Shower room 2nd floot | thermo shwr |  |  |  | 15.03.21 |  | Thermo shower | 39
Kitchen 2n floor 2 | Reliance | 15 | 41 |  | 15.03.21 |  | Relaince | 41
Flat 1 | ? | 22 | 43 | Failed fail safe test | 19.03.21 | TMV replaced, Isos replaced | Imix | 42
Flat 2 | ? | 22 | 50 | Cannot adjust Temp. New TMV required | 19.03.21 | TMV removed by otcs
Flat 4 | Hydromix | 15 | 35 | Cannot adjust Temp. New TMV required | 19.03.21 | TMV replaced | Imix | 39