## Sheet1
Date | Building | Location | Make | Size | Temp. | Comments
2020-06-15 | Foyle Fold | Ground Floor WC | Imix | 15 | 39.5 | Original TMV failed failsafe, replaced.
| Foyle Fold | Laundry | Bossmix | 15 | 43 | Serviced
| Foyle Fold | Kitchen | Imix | 15 | 39 | Serviced
| Foyle Fold | Kitchen | Imix | 15 | 43 | Installed new TMV
| Foyle Fold | Guestroom | Imix | 15 | 42.5 | Original TMV failed failsafe, replaced.
| Foyle Fold | Guestroom | TMV shower |  | 40 | Serviced
| Foyle Fold | Hairdresser | Ausimix | 15 | 42 | Serviced
| Foyle Fold | Hairdresser | Bossmix | 15 | 46 | Serviced
2020-06-16 | Foyle Fold | Room 25 | imix | 15 | 41 | Original TMV failed failsafe, replaced.
| Foyle Fold | Room 25 | imix | 15 | 43 | Installed new TMV
| Foyle Fold | Room 25 | Triton shower |  |  | Cartridge replaced
| Foyle Fold | Room 24 | Imix | 15 | 42 | Original TMV failed failsafe, replaced.
| Foyle Fold | Room 24 | Imx | 15 | 43 | Installed new TMV
| Foyle Fold | Room 24 | Imix | 22 | 42 | washers replaced and serviced
| Foyle Fold | Room 23 | Imix | 22 | 42.7 | washers replaced and serviced
| Foyle Fold | Room 23 | Imix | 15 | 42 | Installed new TMV
| Foyle Fold | Room 23 | Imix | 15 | 43 | Installed new TMV
| Foyle Fold | Room 23 | Bristan shower |  | 40 | Installed new TMV
2020-06-17 | Foyle Fold | Room 26 | Imix | 15 | 43 | Installed new TMV
| Foyle Fold | Room 26 | Imix | 15 | 42 | Original TMV failed failsafe, replaced.
| Foyle Fold | Room 26 | Bristan shower |  | 40 | Serviced
| Foyle Fold | Room 22 | Imix | 15 | 43 | Installed new TMV
| Foyle Fold | Room 22 | Imix | 15 | 42 | original TMV failed failsafe, replaced.
| Foyle Fold | Room 22 | Triton shower |  | 42 | Serviced
| Foyle Fold | Room 34 | Imix | 15 | 42 | original TMV failed failsafe, replaced.
| Foyle Fold | Room 34 | Imix | 15 | 43 | Installed new TMV
| Foyle Fold | Room 34 | TMV shower |  | 38 | Serviced
| Foyle Fold | Room 28 | Imix | 15 | 42 | Original TMV failed failsafe, replaced.
| Foyle Fold | Room 28 | Imix | 15 | 43 | Installed new TMV
| Foyle Fold | Room 28 | Triton shower |  | 39 | Serviced
2020-06-18 | Foyle Fold | Room 30 | Imix | 15 | 43 | Installed new TMV
| Foyle Fold | Room 30 | Imix | 15 | 42 | Original TMV failed failsafe, replaced.
| Foyle Fold | Room 30 | Triton shower |  | 43 | Serviced
| Foyle Fold | Room 31 | Imix | 15 | 43 | Original TMV failed failsafe, replaced.
| Foyle Fold | Room 31 | Imix | 15 | 41.5 | Original TMV failed failsafe, replaced.
| Foyle Fold | Room 31 | Bristan shower |  | 43 | Serviced
| Foyle Fold | Room 32 | Imix | 15 | 43 | Installed new TMV
| Foyle Fold | Room 32 | Imix | 15 | 42 | Original TMV failed failsafe, replaced.
| Foyle Fold | Room 32 | Bristan shower |  | 41 | Serviced
| Foyle Fold | Room 29 | Imix | 15 | 43 | Installed new TMV
| Foyle Fold | Room 29 | Imix | 15 | 42 | Original TMV failed failsafe, replaced.
| Foyle Fold | Room 29 | Triton shower |  | 43 | Serviced
2020-06-19 | Foyle Fold | Room 33 | Imix | 15 | 43 | Installed new TMV
| Foyle Fold | Room 33 | Imic | 15 | 42 | Original TMV failed failsafe, replaced.
| Foyle Fold | Room 33 | TmV shower |  | 43 | Serviced
| Foyle Fold | Room 27 | Imix | 15 | 43 | Installed new TMV
| Foyle Fold | Room 27 | Imix | 15 | 42 | Original TMV failed failsafe, replaced.
| Foyle Fold | Room 27 | Triton shower |  | 39 | Cartridge replaced
| Foyle Fold | 1st Floor Bathroom | Caremix | 22 | 42 | Serviced
| Foyle Fold | 1st Floor Bathroom | Imix | 15 | 42 | Original TMV failed failsafe, replaced.
| Foyle Fold | 1st Floor Bathroom | Mira TMV tap |  | 42 | Serviced
| Foyle Fold | Room 39 | Imix | 15 | 43 | Installed new TMV
| Foyle Fold | Room 39 | Imix | 15 | 42 | Original TMV failed failsafe, replaced.
| Foyle Fold | Room 39 | Bristan shower |  | 40 | Serviced
2020-06-23 | Foyle Fold | Room 35 | Imix | 15 | 43 | Installed new TMV
| Foyle Fold | Room 35 | Imix | 15 | 41 | Original TMV failed failsafe, replaced.
| Foyle Fold | Room 35 | Bristan shower |  | 42 | Serviced
| Foyle Fold | Room 36 | Imix | 15 | 43 | Installed new TMV
| Foyle Fold | Room 36 | Imix | 15 | 41 | Original TMV failed failsafe, replaced.
| Foyle Fold | Room 36 | Triton shower |  | 44 | Serviced
| Foyle Fold | Room 37 | Imix | 15 | 43 | Installed new TMV
| Foyle Fold | Room 37 | Imix | 15 | 42 | Original TMV failed failsafe, replaced.
| Foyle Fold | Room 37 | Imix | 22 | 42 | Original TMV failed failsafe, replaced.
| Foyle Fold | Room 37 | Triton shower |  | 42 | Serviced
| Foyle Fold | Room 38 | Imix | 15 | 43 | Installed new TMV
| Foyle Fold | Room 38 | Imix | 15 | 42 | Original TMV failed failsafe, replaced.
| Foyle Fold | Room 38 | Bristan shower | 15 | 42 | Serviced
| Foyle Fold | Room 40 | Imix | 15 | 43 | Installed new TMV
| Foyle Fold | Room 40 | Imix | 15 | 41 | Original TMV failed failsafe, replaced.
| Foyle Fold | Room 40 | Imix | 15 | 40 | Original TMV failed failsafe, replaced.
| Foyle Fold | Room 41 | Imix | 15 | 43 | Installed new TMV
| Foyle Fold | Room 41 | Imix | 15 | 41 | Original TMV failed failsafe, replaced.
| Foyle Fold | Room 41 | Imix | 22 | 41 | Original TMV failed failsafe, replaced.
| Foyle Fold | Room 42 | Imix | 15 | 42 | Installed new TMV
| Foyle Fold | Room 42 | Imix | 15 | 41 | Original TMV failed failsafe, replaced.
| Foyle Fold | Room 42 | Bristan shower | 15 | 40 | Serviced
2020-06-24 | Foyle Fold | Room 48 | Imix |  | 42 | original TMV failed failsafe, replaced.
| Foyle Fold | Room 48 | Imix | 15 | 43 | Installed new TMV
| Foyle Fold | Room 48 | Triton shower |  | 42 | Serviced
| Foyle Fold | Room 43 | Imix | 15 | 43 | Installed new TMV
| Foyle Fold | Room 43 | Imix | 15 | 41 | Original TMV failed failsafe, replaced.
| Foyle Fold | Room 43 | Triton shower |  | 40 | Serviced
| Foyle Fold | Room 44 | Imix | 15 | 43 | Installed new TMV
| Foyle Fold | Room 44 | Imix | 22 | 42 | Original TMV failed failsafe, replaced.
| Foyle Fold | Room 44 | Imix | 15 | 42 | Original TMV failed failsafe, replaced.
2020-06-25 | Foyle Fold | Room 47 | Imix | 15 | 43 | Installed new TMV
| Foyle Fold | Room 47 | Imix | 15 | 41.5 | Original TMV failed failsafe, replaced.
| Foyle Fold | Room 47 | Triton shower |  | 43 | Installed new TMV
| Foyle Fold | Hatch between 47 + 46 |  |  |  | 22mm Isolation Fitted on mains
| Foyle Fold | Hatch between 47 + 46 |  |  |  | Dead leg removed from Hot water
| Foyle Fold | Room 46 | Imix | 15 | 43 | Installed new TMV
| Foyle Fold | Room 46 | Imix | 15 | 42 | Original TMV failed failsafe, replaced.
| Foyle Fold | Room 46 | Triton shower |  | 43 | Serviced
| Foyle Fold | Room 45 | Imix | 15 | 43 | Installed new TMV
| Foyle Fold | Room 45 | ? | ? | 41 | TMV Tiled in - no access
| Foyle Fold | Room 45 | Triton shower |  | 40 | Serviced
| Foyle Fold | Hatch 45 |  |  |  | 22mm Isolation Fitted on mains
| Foyle Fold | Room 55 |  |  |  | No access
| Foyle Fold | Room 56 |  |  |  | No access
| Foyle Fold | Hatch 57 |  |  |  | 22mm isolation fitted to mains
| Foyle Fold | Room 57 | imix | 15 | 43 | Installed new TMV
| Foyle Fold | Room 57 | imix | 15 | 42 | Original TMV failed failsafe, replaced.
| Foyle Fold | Room 57 | Bristan Shower |  | 42 | Serviced
| Foyle Fold | Room 57 | Bristan shower |  |  | Shower head replaced
2020-06-26 | Foyle Fold | Room 54 | Imix | 15 | 43 | Installed new TMV
| Foyle Fold | Room 54 | Imix | 15 | 39 | Original TMV failed failsafe, replaced.
| Foyle Fold | Room 54 | Triton Shower |  | 43 | Serviced
| Foyle Fold | Hatch between 54 + 53 |  |  |  | 22mm isolation fitted to mains
| Foyle Fold | Room 53 | imix | 15 | 43 | Installed new TMV
| Foyle Fold | Room 53 | imix | 15 | 41 | Original TMV failed failsafe, replaced.
| Foyle Fold | Room 53 | Triton shower |  | 43 | Serviced
| Foyle Fold | Room 58 | imix | 15 | 43 | Installed new TMV
| Foyle Fold | Room 58 | imix | 15 | 42 | Original TMV failed failsafe, replaced.
| Foyle Fold | Room 58 | Sirrus Shower |  | 42 | Serviced
2020-06-29 | Foyle Fold | Room 49 | imix | 15 | 43 | Installed new TMV
| Foyle Fold | Room 49 | imix | 15 | 42 | Original TMV failed failsafe, replaced.
| Foyle Fold | Room 49 | Triton Shower |  | 43 | Serviced
| Foyle Fold | Room 50 | imix | 15 | 43 | Installed new TMV
| Foyle Fold | Room 50 | imix | 15 | 42 | Original TMV failed failsafe, replaced.
| Foyle Fold | Room 50 | Triton Shower |  | 43 | serviced
| Foyle Fold | Room 51 | imix | 15 | 43 | Installed new TMV
| Foyle Fold | Room 51 | imix | 15 | 42 | Original TMV failed failsafe, replaced.
| Foyle Fold | Room 51 | Triton Shower |  | 43 | Serviced
| Foyle Fold | Room 52 |  |  |  | No access